## Iteration Mapping Key
|  | Iteration Mapping Key |  |  |  | Quality Assurance Department
Purpose | Through this document, you will be able to see all of the results and the details for all of the testing that has been done so far for the following iteration ID.
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Version |  |  | Project Start Date |  | Project Finish Date
1.0 |  |  | 1 |  |  | 2017-05-07 |  | 2017-05-11
Iteration start date |  |  |  |  | Iteration Finish date
2017-05-07 |  |  |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Cases Report
Test CaseID# | Test Case name | Testing Method | Testing Type | Test Engineer | Machine Type | Failed Test Steps | Passed Test Steps | Test case score | Test Case status | Defect Type | Severity | Actual time | Actual Cost
1.0 | Installation | Manual | Unit testing | Mohamed Sharaf | Laptop | 4 | 4 | 50% | Fail | Functional | Critical | 0:00 | 0
2.0 | AddMachine | Manual | Unit testing | Mohamed Sharaf | Laptop | 7 | 0 | 0% | Fail | Functional | Critical | 0:00 | 0
3.0 | FieldsMappingPage | Manual | Unit testing | Mohamed Sharaf | Laptop | 0 | 1 | 100% | Pass |  |  | 0:00 | 0
4.0 | EventsMapping | Manual | Unit testing | Mohamed Sharaf | Laptop | 0 | 0 |  |  |  |  | 0:00 | 0
5.0 | SettingsScreen | Manual | Unit testing | Mohamed Sharaf | Laptop | 1 | 1 | 50% | Fail | Functional | Critical | 0:00 | 0
6.0 | ErrorHandelingPage | Manual | Unit testing | Mohamed Sharaf | Laptop | 1 | 0 | 0% | Fail | Functional | Critical | 0:00 | 0
7.0 | LogScreen | Manual | Unit testing | Mohamed Sharaf | Laptop | 0 | 0 |  |  |  |  | 0:00 | 0
Iteration Analysis |  |  |  |  | Areas of improvements and corrections
Iteration Status |  | Fail
Total of test cases |  | 7
Total of Critical Test Cases |  | 4
Total of Passed Test Cases |  | 1
Total of Failed Test Cases |  | 4
Automated Test Cases |  | 0
Manual Test Cases |  | 7
Total Actual time |  | 0:00
Total Actual cost |  | 0
Note on G17: Mohamed Sharaf: 01117779538

## 1.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Fail | Function is sent back to the development team
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | Installation |  |  | Test Case ID# |  |  | 1
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-07 |  |  |  |  | Unit testing
Process |  | Test all of the possible scenarios that could happen during the installation steps.
Pre-Conditions |  | The OTMS is not installed and there are no database attached to the SQL server.
Post Conditions |  | The OTMS is installed and there is a database attached to the SQL server.
Needed Credentials |  | Testing environment that achieve the minimum requirements for the OTMS.
Test Case Inputs |  | 1- 192.168.1.1, test, test 2- //";A!@#, //";A!@#, //";A!@# 3- 11111111111111111111111111111111111111111111, 1111111111111111111111AAAAAAAAAAA, 11111111111111SSSSSSSSSSSS 4- 192.168.1.1, XY, 00, ERPFM 5- //";;:!@#$AS, //";;:!@#$AS, //";;:!@#$AS. 6- 1111111111111111111111111111111111111111111, 11111111111111111111111111, 111111111111111111111111, 1111111111111111111111111111 7- 800, test, test
Additional Information |  | TestInformation_Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | Start the installation. |  | Double click the exe file that is delivered in the otms package. |  | OTMS installation starts. |  | As expected. |  | Pass
2 | LicenseAgreement |  | Read the agreement and click next. |  | DB information screen opens. |  | As expected. |  | Pass
3 | DBInformation |  | Enter test inputs 1, 2, 3. |  | Application accepts inputs 1 only and rejects the rest. |  | Application accepted all kinds of inputs. |  | Fail | Functional | Input validation.
4 | SAPServerConfig |  | Enter test inputs 4, 5, 6. |  | Application accepts inputs 4 only and rejects the rest. |  | Application accepted all kinds of inputs. |  | Fail | Functional | Input validation.
5 | SAPSystemConfig |  | Enter test inputs 7, 8, 6. |  | Application accepts inputs 7 only. |  | Application accepted all kinds of inputs. |  | Fail | Functional | Input validation.
6 | DatabaseConig |  | Choose new database. |  | Database is attached to the right server information. |  | As expected. |  | Pass
7 | MachineReader |  | Choose the ZKTeco and click next. |  | Application finishes configration and summarize up info by showing the confirm installation screen. |  | Application showed the biostart settings although it was not selected. |  | Fail | Logical Flow
8 | Confirm post condition. | [5 empty] | Post condition confirmed. |  | Pass
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 4 |  | Test Case Score |  |  | 50% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 4 |  | Test Case Status |  |  | Fail |  |  | Actual Test time | 0:00
Defect Type |  | Functional |  | Failure Level |  |  | Critical |  |  | Estimated Cost | 0
| Severity |  |  | Critical | [5 empty] | Actual Cost | 0

## 2.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Fail | Function is sent back to the development team
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | AddMachine |  |  | Test Case ID# |  |  | 2
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-07 |  |  |  |  | Unit testing
Process |  | Test all of the possible scenarios for the add machine screen.
Pre-Conditions |  | 1- ECS OTMS is running.
Post Conditions |  | 1- A machine with the name test is added. 2- Machine information added with the IP 192.168.1.3
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs |  | 1- Testname. 2- Empty Entries. 3- ";; -- // 4- 01, 192.168.1.3, testcity, testbuilding, testsection, 00, VPN, Active 5- 01, 192.168.1.3 -t, '; -- //, '; -- //, '; -- //, T'; -- //, 00, VPN, Active 6- Empty entries. 7- 01, 192.168.1.1 -t, testcity, testbuilding, testsection, 00, VPN, active
Additional Information |  | TestInformation_Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | AddMachine function |  | Select add machine, enter test inputs 1, 2, 3 and click save. |  | Application accepts inputs 1 and rejects the rest. |  | Application accepted inputs 1, 3. |  | Fail | Functional
2 | MaintainHandpunchMachines |  | Click the button at the bottom of the page, enter test inputs 4, 5, 6. |  | Application accepts inputs 2 only and rejects the rest. |  | Application accepted all of the inputs. |  | Fail | Functional
3 | MaintainHandpunchMachines |  | Repeat step 2 with test inputs 7. |  | Application rejects inputs. |  | A popup message appears saying wrong inputs. However, I can close it and leave the inputs as they are. |  | Fail | Functional
4 | TestConnection |  | click on the test connection button for each of the inputs from 4 to 7. |  | Does not connect with any IP except for inputs 4. |  | Application crashed with inputs 5 and 7. |  | Fail | SW_Bug
5 | Select/DeselectAllButton | [5 empty] | This button functionality is marking all of the connections as active not selecting the entries. |  | Fail | Functional | Naming or functionality error. If the functionality is right, it should be Activate all not select all.
6 | UndoButton | [5 empty] | The button cancels all of the changes that were made after the last save. |  | Fail | Functional | If the user clicked on the button by mistake after entring about 50 record. All of his/her work will be gone.
7 | SavButton | [5 empty] | It checks the inputs for valid or invalid inputs and doesnot save unless all of them are correct. |  | Fail | Functional | No input validation except on the IP
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 7 |  | Test Case Score |  |  | 0% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 0 |  | Test Case Status |  |  | Fail |  |  | Actual Test time | 0:00
Defect Type |  | Functional |  | Failure Level |  |  | Critical |  |  | Estimated Cost | 0
| Severity |  |  | Critical | [5 empty] | Actual Cost | 0

## 3.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Pass | No Action Needed
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | FieldsMappingPage |  |  | Test Case ID# |  |  | 3
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-08 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for FieldsMapping screen.
Pre-Conditions |  | 1- OTMS application is running. 2- A machine is added and saved.
Post Conditions
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs |  | 1- Personnel number, 6, 8. 2- Terminal ID, 0, 4. 3- Terminal ID, 15, 4. 4- Order number, 0, 4. 5- ";;, ";;//, ";;//.
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | AddMappingEntry |  | Click on Fields Mapping button, select a valid machine name, enter test inputs 1, 2, 3. |  | Application accepts 1, 2 and rejects 3, 4. |  | As expected. |  | Pass | Logical Flow | No error message with test inputs 5.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 0 |  | Test Case Score |  |  | 100% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 1 |  | Test Case Status |  |  | Pass |  |  | Actual Test time | 0:00
Defect Type |  | #N/A |  | Failure Level |  |  | N/A |  |  | Estimated Cost | 0
| Severity |  |  | #N/A | [5 empty] | Actual Cost | 0

## 4.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | #DIV/0! | #DIV/0!
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | EventsMapping |  |  | Test Case ID# |  |  | 4
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-08 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for the Events mapping page.
Pre-Conditions |  | OTMS application is running.
Post Conditions
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | No data to test.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 0 |  | Test Case Score |  |  | #DIV/0! |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 0 |  | Test Case Status |  |  | #DIV/0! |  |  | Actual Test time | 0:00
Defect Type |  | #N/A |  | Failure Level |  |  | #DIV/0! |  |  | Estimated Cost | 0
| Severity |  |  | #N/A | [5 empty] | Actual Cost | 0

## 5.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Fail | Function is sent back to the development team
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | SettingsScreen |  |  | Test Case ID# |  |  | 5
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-08 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for the settings Screen.
Pre-Conditions |  | OTMS application is running.
Post Conditions |  | Settings changes.
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs |  | 1- 192.168.1.1, 800, EB7, ecsotms, 00, ecsotms 2- #@~!ABC123.";;)(
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | ChangeSettings |  | Enter test case inputs 1 in the settings form in the following order: from left to right and then from top to down. Once done, click save. |  | Application accepts inputs normally. |  | As expected. |  | Pass
2 | Change settings |  | Repeat step 1 with test inputs 2 in the same order and in all of the boxes. |  | Application rejects all of the inputs. |  | Application accepted all of the inputs normally. |  | Fail | Functional
3 | [9 empty] | Functional
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 1 |  | Test Case Score |  |  | 50% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 1 |  | Test Case Status |  |  | Fail |  |  | Actual Test time | 0:00
Defect Type |  | Functional |  | Failure Level |  |  | Critical |  |  | Estimated Cost | 0
| Severity |  |  | Critical | [5 empty] | Actual Cost | 0

## 6.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Fail | Function is sent back to the development team
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | ErrorHandelingPage |  |  | Test Case ID# |  |  | 6
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-11 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for the error handeling page.
Pre-Conditions |  | OTMS application is running.
Post Conditions
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs |  | 1- Redundant Data. 2- Conflicted Data as follows: - Check In time is after check out. - Break in after check out. - Break out before check in.
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | Submit records with errors of all of the test inputs. |  | Do the update procedure from sap and then post the updates to the records. |  | Application returns all of the test case inputs as errors. |  | Application uploaded all of the time frames and only validates the date. |  | Fail | Functional
2 | [9 empty] | Functional
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 1 |  | Test Case Score |  |  | 0% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 0 |  | Test Case Status |  |  | Fail |  |  | Actual Test time | 0:00
Defect Type |  | Functional |  | Failure Level |  |  | Critical |  |  | Estimated Cost | 0
| Severity |  |  | Critical | [5 empty] | Actual Cost | 0

## 7.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | #DIV/0! | #DIV/0!
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | LogScreen |  |  | Test Case ID# |  |  | 7
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-11 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for the log page.
Pre-Conditions |  | OTMS application is running.
Post Conditions
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | Check the log retrieval
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 0 |  | Test Case Score |  |  | #DIV/0! |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 0 |  | Test Case Status |  |  | #DIV/0! |  |  | Actual Test time | 0:00
Defect Type |  | #N/A |  | Failure Level |  |  | #DIV/0! |  |  | Estimated Cost | 0
| Severity |  |  | #N/A | [5 empty] | Actual Cost | 0

## 8.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Pass | No Action Needed
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | Download from SAP server |  |  | Test Case ID# |  |  | 8
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-08 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for downloading info from sap.
Pre-Conditions |  | OTMS application is running. SAP connection RFC is successful.
Post Conditions
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs |  | 1- All of SAP related information.
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | Dowload process. | [5 empty] | Operation successful. |  | Pass
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 0 |  | Test Case Score |  |  | 100% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 1 |  | Test Case Status |  |  | Pass |  |  | Actual Test time | 0:00
Defect Type |  | #N/A |  | Failure Level |  |  | N/A |  |  | Estimated Cost | 0
| Severity |  |  | #N/A | [5 empty] | Actual Cost | 0

## 9.0
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | Pass | No Action Needed
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  | UploadProcess |  |  | Test Case ID# |  |  | 9
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-08 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for the upload operation.
Pre-Conditions |  | OTMS application is running and the RFC connection is connected.
Post Conditions |  | Data uploaded to SAP successfully.
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs |  | Upload all of the available records.
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1 | Upload operation. | [5 empty] | Upload process successful. |  | Pass
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 0 |  | Test Case Score |  |  | 100% |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 1 |  | Test Case Status |  |  | Pass |  |  | Actual Test time | 0:00
Defect Type |  | #N/A |  | Failure Level |  |  | N/A |  |  | Estimated Cost | 0
| Severity |  |  | #N/A | [5 empty] | Actual Cost | 0

## Temp
|  | Test Case |  |  |  | Quality Assurance Department
[11 empty] | Test Case Status | Advised Action
Purpose | Through this document, you will be able to see all the details and results for the following test case. | [9 empty] | #DIV/0! | #DIV/0!
Project Information
Project Name |  |  |  | Project ID# |  |  | Project type
OTMS |  |  |  | 1 |  |  | EXE
Iteration ID# |  |  | Project Start Date |  |  | Project Finish Date
1.0 |  |  | 2017-05-07 |  |  | 2017-05-11
Product Manager |  |  |  |  | Technical Admin
0 |  |  |  |  | Heba Nour-Eldin
Additional Information |  |  | ProjectInformation_AdditionalInformation
Test Information
Test Case name |  |  |  |  | Test Case ID#
Testing Method |  | Manual |  |  | Test Engineer |  |  | Mohamed Sharaf
Date of execution |  |  |  |  | Testing Type
2017-05-08 |  |  |  |  | Unit testing
Process |  | Testing all of the possible scenarios for
Pre-Conditions |  | OTMS application is running.
Post Conditions
Needed Credentials |  | 1- Access to the server: 192.168.1.37. 2- Hegaz VPN access.
Test Case Inputs
Additional Information
Test Environment
Operating System |  |  | OS version |  |  | Framework Version
Windows |  |  | Windows 7 |  |  | 4.6
RAM Capacity |  | 4 GB |  | Hard Drive type |  | HDD | Hard Drive Capacity |  | 512 GB
Processor Type |  | Dual Core |  | Processor Clock Speed |  |  | 1.7
Machine type |  | Laptop |  | Screen size |  | 15 | Screen Resolution |  | 1080P
Additional Information |  | TestEnvironment_Additional Information
Test Steps
Step ID# | Process / Transaction |  | Detailed Step |  | Expected Result |  | Actual Result |  | Step Status | Defect Type | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Test Case Detailed Results
Total Failed Steps |  | 0 |  | Test Case Score |  |  | #DIV/0! |  |  | Estimated Test time | 0:00
Total Passed Steps |  | 0 |  | Test Case Status |  |  | #DIV/0! |  |  | Actual Test time | 0:00
Defect Type |  | #N/A |  | Failure Level |  |  | #DIV/0! |  |  | Estimated Cost | 0
| Severity |  |  | #N/A | [5 empty] | Actual Cost | 0